## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Pearl Gecko Board Stops Working Again | 1 | 100 | 100 | 2021-10-31 | Mitigated | M | I got my board's boot loader to start working again
LCD output is too fast to see | 3 | 20 | 60 | 2021-10-31 | Accepted | A | I've never worked with the LCD display before, but will learn quickly
I haven't dealt with Mechanics in awhile | 2 | 8 | 16 | 2021-10-31 | Accepted | A | I can re-learn what I'll need quickly
The system is too sensitive to play | 13 | 40 | 520 | 2021-10-31 | Accepted | A | I will learn about how I can make the system less sensitive as I develop
Computer/Hard Drive will die again | 1 | 100 | 100 | 2021-11-09 | Mitigated | M | I downloaded a lot of driver firmware and ran tests to ensure my device is healthy
My LED duty cycle won't be correct due to task interference | 20 | 5 | 100 | 2021-11-09 | Accepted | A | I can increase its priority
My project will get deadlocked if not initialized correctly | 5 | 100 | 500 | 2021-11-11 | Mitigated | M | Any task that acquires a mutex lock only uses it extremely briefly
Segger won't work | 100 | 100 | 10000 | 2021-12-07 | Accepted | A | I decided to debug without the use of segger
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100